Milestones and Project Outputs

| Mile-stone | Due Date | Activities/Output |
| --- | --- | --- |
| 0 | 07/30/06 | Signing the Contract: Project Agreement Signed by the Project Team, Project Partner, and the World Bank Country Director |
| 1 | 1/30/07 | Milestone 1: Questionnaire & methodology for data collection, relevant census data and maps Sample maps and census data Submit 1st and 2nd standard GAPFund progress report to Project Liaison and GAPFund Contact (October 15, 2006 and January 15, 2007) |
| 2 | 07/30/07 | Milestone 2: GIS spatial bookmarking tools and KM tools Agenda, participant lists and outcomes report on capacity building workshops for community and stakeholders Web-based M&E tools M&E tool handbook Agenda, participant lists, materials and outcomes report on M&E tools training Copy of proposal submitted for follow-on funding Revenue model Submit 3rd and 4th standard GAPFund progress report to Project Liaison and GAPFund Contact (April 15, 2007 and July 15, 2007) |
|  | Submit Project Completion Report and hold a Completion Interview with Project Liaison |